## Sheet1
Task | Project Team Member(s) | Responsible (R) | Accountable (A) | Consulted (C) | Informed (I)
Design and Planning | Project Team | Project Team | Project Lead | Stakeholders, Project Manager | -
Develop Bus Matrix | Data Analyst | Data Analyst | Project Lead | Stakeholders | Project Team
Develop Use Cases/User Stories | Business Analyst | Business Analyst | Project Lead | Stakeholders | Project Team
Develop Dimensional Model Matrix | Data Engineer | Data Engineer | Project Lead | Stakeholders | Project Team
Develop ETL Instructions | Data Engineer | Data Engineer | Project Lead | Stakeholders | Project Team
Develop Conceptual Data Model | Data Architect | Data Architect | Project Lead | Stakeholders | Project Team
Develop Logical Data Model | Data Architect | Data Architect | Project Lead | Stakeholders | Project Team
Develop Physical Data Model | Data Engineer | Data Engineer | Project Lead | Stakeholders | Project Team
Develop Architecture Diagram | Solution Architect | Solution Architect | Project Lead | Stakeholders | Project Team
Develop Data Dictionary | Data Engineer | Data Engineer | Project Lead | Stakeholders | Project Team
Develop High Level Project Plan | Project Manager | Project Manager | Project Lead | Stakeholders | Project Team
Development of Warehouse Solution | Development Team | Development Team | Project Lead | Stakeholders | Project Team
Develop ETL Orchestration Service | Data Engineer | Data Engineer | Project Lead | Stakeholders | Project Team
Develop Code or Scripts | Development Team | Development Team | Project Lead | Stakeholders | Project Team
Testing and Quality Assurance | QA Analyst | QA Analyst | Project Lead | Stakeholders | Project Team
Visualization | Data Visualization Team | Visualization Team | Project Lead | Stakeholders | Project Team
Executive Presentation | Project Team | Project Team | Project Lead | Stakeholders | Project Team
Task | Nivetha (Data Architect) | Vidhika (Data Engineer) | Akshay (Project Management) | Asish (Data Analyst)
End-to-end data management | R | - | - | -
Data sourcing and structuring | R | - | - | -
Design of data warehouse architecture | R | - | - | -
Alignment with project objectives | R | - | - | -
Implementation of data warehouse solution | R | - | - | -
Data pipeline implementation | - | R | R | -
ETL process development | - | R | R | -
Optimization of data workflows | C | R | R | -
Reliability and scalability | - | R | R | -
Data analysis | - | - | - | R
Visualization and reporting | - | - | - | R
Collaboration with stakeholders | - | - | - | R
Actionable recommendations | - | - | - | R
In this RACI matrix:
R denotes that the individual is responsible for the task.
C denotes that the individual is to be consulted for the task.
"-" denotes that the individual is not directly involved in the task.
Each task has been assigned the appropriate individual based on their role and responsibilities.
getting the data
data profilling
transformation of data
merging
phsysical layout
ER diagram
AWS archi
future enhancement
Visualization and reporting
Executive Presentation

## Sheet2
Task | Nivetha | Vidhika | Akshay | Asish | Dates
Getting the data | R | C | I | I | Done
Data profiling | I | I | R | C/I | April5-10
Transformation of data | C | R | I | I | April5-10
Merging | C | R | I | I | April5-10
Physical layout | R | I | I | C/I | April10-20
ER diagram | R | I | C/I | C/I | April10-20
AWS architecture | R | C/I | C/I | C/I | April10-20
Future enhancement | I | R | C | I | April 20- 30
Visualization and reporting | C/I | C/I | R | R | May 1st week
Executive Presentation | R | R | R | R
R" denotes that the individual is responsible for the task.
C denotes that the individual is to be consulted for the task.
A denotes that the individual is accountable for the task.